IMPLEMENTATION OF LOCAL COMPETITION

CONSENSUS REPORT

GROUP:	Co-location Group

DATE SUBMITTED: 	September 13, 2001

REPORT #: 		CLRE021C

TITLE:	Co-location Ordering Intervals – Revised Service Categories and Delivery Timelines

OUTCOME:		CONSENSUS

Following industry discussions at the Co-location Ordering Intervals Sub-working Group and in consideration of TIF CLTF003, members of the Coalition for Better Co-location (“CBC”), TELUS (“TCI”), and Bell Canada et al (including BELL Canada, MTS, SaskTel, and Aliant) agree to amend co-location terms and conditions relating to co-location ordering intervals.

### OVERVIEW

Co-location Ordering Intervals are redefined herein and categorized according to agreed upon service types and delivery requirements.

Revisions have been achieved for all service types.

- REVISONS TO SERVICE CATEGORIES

For the purpose of refining delivery intervals, co-location services are categorized according to the following matrix:

| Service Category | Description |
| --- | --- |
| New Build – Type 1A / 1B | Segregated co-location room where the applicant is new to the Central Office location. Type 1A – Segregated Space & Segregated Entrance* Type 1B – Segregated Space & Common Entrance* * Refer to Co-location Entrant Information Package. |
| New Build – Type 2 | Type 2 - Unsegregated co-location space dedicated to the applicant where the applicant performs the installation and maintenance. |
| New Install – Virtual | Unsegregated co-location space dedicated to the applicant where the ILEC performs the installation and maintenance. |
| Rearrangement – Power | Upgrade / Downgrade of existing power facilities provisioned for the applicant. |
| Rearrangement – Infrastructure | Upgrade / Downgrade of existing infrastructure, including items like: HVAC rebalance, overhead racking work, alteration to co-location room dimensions. |
| Add Equipment – Type 1A / 1B / 2 | Circumstances where an applicant wishes to install approved equipment into licensed space (I.e. Equipment is approved for Co-location by the ILEC). |
| Connecting Links – All Types | Subsequent requests for DS0 Type A/B, DS1 Type C, DS3 and IC to IC links. |

- GENERAL IMPROVEMENTS & QUALIFIERS

To meet revised service delivery intervals outlines in this consensus, the following general improvements and qualifiers will be observed:

General Qualifiers

Co-locator may waive Phase 1 & pre-approve Phase 2 costs up to $15K to achieve condensed intervals.

All intervals begin based on the Application Date.

Extensions for report approval of up to 10 working days are available; however, the interval clock stops during this period.

Co-locators commit to meeting all Engineering requirements contained in the Planning Addendum(s) prior to beginning Phase 2 (Standard Intervals) or Phase 1 (Condensed Intervals).

Co-locators provide complete design and implementation packages with all requests for Virtual Co-location.

Co-locators provide forecasts for new builds as well as incremental activity, upon request from the ILEC and/or as otherwise agreed to within the CISC NOSWG/BPSWG.

Exceptional circumstances, such as industry-wide material shortages or unforecasted work volume, may impact the Companies ability to deliver co-location services within the intervals contained in this consensus. The Companies shall, however, make every effort to make such arrangements available upon request.

- LEGAL DOCUMENTS / REVISIONS TO COLA

COLA amendments to be completed and filed with the Commission by end of December 2001.

- EFFECTIVE DATE

Upon approval of this consensus by the Commission.

** END **

APPENDIX #1: REVISED INTERVAL MATRICES

TABLE 1 – STANDARD SERVICE DELIVERY

|  | New Build - Type 1A / 1B | New Build - Type 2 | New Install - Virtual | Rearrangement - Infrastructure | Rearrangement - Power | Connecting Links |
| --- | --- | --- | --- | --- | --- | --- |
| Application to Initial Report | 10 | 10 | 10 | 10 | 10 | 10 |
| Applicant Approval Interval | 5 | 5 | 5 | 5 | 5 | 5 |
| Initial Report Approval to Secondary Report | 25 | 25 | 25 | 25 | 20 | 15 |
| Applicant Approval Interval | 5 | 5 | 5 | 5 | 5 | 5 |
| Secondary Report Approval to Effective Date | 55 | 35 | 35 | 35 | 30 | 15 |
| Total Interval w/d (Est Calendar) | 100 w/d*** (5 months) | 80 w/d (4 months) | 80 w/d (4 months) | 80 w/d (4 months) | 70 w/d (3.5 months) | 50 w/d (2.5 months) |

TABLE 2 – CONDENSED SERVICE DELIVERY (Pre-approval of Phase 2 Costing)

|  | New Build - Type 1A / 1B* | New Build - Type 2 | New Install - Virtual | Rearrangement - Infrastructure | Rearrangement - Power | Connecting Links |
| --- | --- | --- | --- | --- | --- | --- |
| Application w/ Pre-approved Phase 2 to Secondary Report | 35 (Manhole Locations in 15 w/d)** | 30 (Manhole Locations in 15 w/d)** | 30 (Manhole Locations in 15 w/d)** | 30 | 20 | 15 |
| Applicant Approval Interval | 5 | 5 | 5 | 5 | 5 | 5 |
| Secondary Report to Effective Date | 55 | 35 | 35 | 35 | 30 | 15 |
| Total Interval w/d (Est Calendar) | 95 w/d (4.75 months) | 70 w/d (3.5 months) | 70 w/d (3.5 months) | 70 w/d (3.5 months) | 55 w/d (2.75 months) | 35 w/d (1.75 months) |

* For Type 1A/1B and Type 2 Co-location Intervals where Phase 1 is waived (Table 2), pre-selection site tours will not be made available.  Additionally, floorplans or bay layout arrangements will be provided with the Secondary Report.

** Although no Initial Report is provided, the ILEC will issue the Meet-me Manhole location(s) to the Applicant within 15 w/d of the application date.

*** W/D = Refers to regular work-days.